EXPIRATION TRACKER v1

Solo Development Schedule

10:00 AM – 12:30 PM daily  |  Thursdays 10:00 AM – 2:00 PM  |  Sundays 10:00 AM – 12:00 PM  |  No days off

| 92 Days Jun 11 – Sep 10 | No Days Off All 7 days | 245 Hours Estimated total | 8 Phases 0 through 7 |
| --- | --- | --- | --- |

| Phase 0 Setup | Phase 1 Console App | Phase 2 Database | Phase 3 GUI | Phase 4 Search/Sort | Phase 5 Optimization | Phase 6 OCR | Phase 7 Finalization |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Mon / Tue / Wed / Fri / Sat 10:00 AM – 12:30 PM 2.5 hours | Sunday 10:00 AM – 12:00 PM 2 hours (lighter) | Thursday 10:00 AM – 2:00 PM 4 hours (deep work) |
| --- | --- | --- |

| Phase 0 | Setup + Fundamentals |
| --- | --- |

| THU 06/11 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Install Java JDK 17 + IntelliJ IDEA. Create a new JavaFX project. Run 'java -version' in terminal to confirm it works. Create the GitHub repository. Read through the full project blueprint so you understand what you are building. |
| --- | --- |

| FRI 06/12 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: Variables and Data Types. Open IntelliJ and write 10 small practice programs — one that stores a product name in a String, one that stores a quantity in an int, one that stores today's date using LocalDate.now(). Run each one and confirm the output. |
| --- | --- |

| SAT 06/13 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: Classes and Objects. Write the Product class with all 7 fields: id (int), name (String), category (String), quantity (int), purchaseDate (LocalDate), expirationDate (LocalDate), notes (String). No constructor yet — just the fields. Understand: this class is the blueprint for every product in the app. |
| --- | --- |

| SUN 06/14 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Learn: Constructors. Add a constructor to Product that accepts all fields as parameters and assigns them. Test it in a main() method by creating 3 different Product objects and printing their names to confirm it works. |
| --- | --- |

| MON 06/15 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: Methods. Add the getDaysUntilExpiration() method to Product — it uses ChronoUnit.DAYS.between(LocalDate.now(), expirationDate) to calculate days left. Add a second method: getStatus() that returns the String 'EXPIRED', 'URGENT', 'WARNING', or 'SAFE' based on days remaining. |
| --- | --- |

| TUE 06/16 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: Exception Handling. Write a helper method called parseDate(String input) that wraps LocalDate.parse() in a try-catch block. If the input is invalid, it prints a clear error message and returns null instead of crashing the program. Test it with 5 different inputs: a valid date, letters, an empty string, a number, and a wrong format. |
| --- | --- |

| WED 06/17 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: Git branching. Practice the full workflow: create a branch called 'feature/product-class', make a small edit, commit it, push the branch, then merge it back to main. This is the workflow you will use for every feature from now on. Learn: ArrayList — write a short program that creates an ArrayList<Product>, adds 3 products, loops through them, and prints each name. |
| --- | --- |

| THU 06/18 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Design the database structure on paper first. Draw the products table: every column name, its data type (TEXT, INTEGER), and mark which is the primary key. Then write the CREATE TABLE SQL statement in a file called schema.sql. Sketch all 3 UI screens on paper: Dashboard, Inventory Table, and Add/Edit Form. Label every button, field, and column you plan to include. |
| --- | --- |

| FRI 06/19 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Create the project folder structure inside IntelliJ: src/main/java/model (for Product.java), src/main/java/service (for InventoryService.java later), src/main/java/database (for ProductDAO.java later), src/main/java/ui (for all JavaFX screens later). Move Product.java into the model folder. Fix any import errors that result. |
| --- | --- |

| SAT 06/20 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) PHASE 0 REVIEW. Read through every file you have written so far. Ask yourself: do I understand every line? For any line you do not fully understand, look it up or rewrite it in a simpler way. Clean up Product.java — remove any test main() code, make sure all fields are properly named. Commit everything cleanly to GitHub with message 'Phase 0 complete: Product model, exception handling, folder structure'. |
| --- | --- |

| SUN 06/21 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Consolidation day. Write the CREATE TABLE SQL for both tables (products and product_batches) from memory — without looking. Then check your answer against the schema.sql file. Review your UI sketches and add any detail you missed. Confirm GitHub repo is clean and up to date. |
| --- | --- |

| Phase 1 | Console Application |
| --- | --- |

| MON 06/22 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Create InventoryService.java in the service package. Create an ArrayList<Product> field called inventory. Write the addProduct(String name, String category, int qty, LocalDate expDate) method — it creates a new Product object and adds it to the ArrayList. Test it in a temporary main() method: add 2 products and print their names. |
| --- | --- |

| TUE 06/23 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Write viewAllProducts() in InventoryService. It loops through the ArrayList and prints each product as: '[0] Milk ¦ Dairy ¦ Qty: 2 ¦ Expires: 2026-06-20 ¦ Days left: 3 ¦ Status: URGENT'. If the list is empty, print 'No products in inventory.' Test with 3 manually added products. |
| --- | --- |

| WED 06/24 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Write deleteProduct(int index) in InventoryService. It removes the product at that ArrayList index. In ConsoleApp, add menu option 3 (Delete): show all products with their index numbers, ask the user to type an index, then ask 'Are you sure? (y/n)' before deleting. If they type anything other than 'y', cancel the deletion. |
| --- | --- |

| THU 06/25 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Write editProduct(int index, int newQty, LocalDate newExpDate, String newNotes) in InventoryService. Add menu option 4 (Edit): show all products, ask which index to edit, then ask for new values one at a time. If the user presses Enter without typing anything for a field, keep the existing value — do not overwrite it with blank. Add input validation: quantity must be positive, date must parse without error. |
| --- | --- |

| FRI 06/26 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: Linear Search. Write findProductsByName(String query) in InventoryService. It loops through the ArrayList and returns a new ArrayList of all products whose name contains the query string (case-insensitive). Add menu option 5 (Search): user types a name, matching products are displayed with their index numbers. |
| --- | --- |

| SAT 06/27 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Write getExpiringProducts(int withinDays) — returns all products with 0 < daysLeft <= withinDays and quantity > 0. Write getExpiredProducts() — returns all products where daysLeft <= 0. Add menu option 6 (Show Expiring Soon) and option 7 (Show Expired). Test both with a mix of expired, urgent, and safe products. |
| --- | --- |

| SUN 06/28 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Add a Category enum in the model package with values: DAIRY, PRODUCE, CANNED_GOODS, MEDICINE, COSMETICS, BEVERAGES, SNACKS, OTHER. Update Product to use Category instead of String. Update addProduct() and the menu to use the enum. When adding a product, display the categories as numbered options. |
| --- | --- |

| MON 06/29 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Write filterByCategory(Category cat) in InventoryService. Add menu option 8 (Filter by Category): display the category list, user picks one, app shows only products in that category. Also add a 'mark as used' option (option 9) that decrements a product's quantity by 1. When quantity hits 0, print a warning: 'This product is now out of stock.' |
| --- | --- |

| TUE 06/30 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Full manual test run. Use the console app as if you are a real user for 25 minutes. Scenario: go grocery shopping (add 8 products), check what's expiring soon, edit the quantity of two items, delete one expired item, search for 'milk'. Write down every bug, weird behavior, or confusing message you encounter. |
| --- | --- |

| WED 07/01 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Fix all remaining bugs from yesterday. Then improve the output formatting: use String.format() to align columns when printing the product list so everything lines up neatly. Add a separator line (=====) between sections. Make error messages consistent: they should all start with 'Error:' so users recognize them. |
| --- | --- |

| THU 07/02 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Learn: Modular programming. Review InventoryService.java — is it too long? If any method is longer than 35 lines, break it into smaller helper methods. Add meaningful comments to every method explaining what it does and what each parameter means. Write down: what concepts have you used so far? (Classes, constructors, methods, ArrayList, exception handling, enums, linear search.) |
| --- | --- |

| FRI 07/03 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Stress test the app. Try every way to break it: type letters in quantity field, type a date in the wrong format, enter a negative index, add a product with an empty name, enter a date that has already passed. For each crash or wrong behavior, write the fix and apply it. The app should never crash no matter what the user types. |
| --- | --- |

| SAT 07/04 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) PHASE 1 WRAP-UP. Every feature must work: add, view, edit, delete, search, filter, expiring/expired views, mark-as-used. Do one final full test. Clean up all code. Push to GitHub with message 'Phase 1 complete: full console CRUD app with search, filter, validation'. The console app is your foundation — it must be solid before building on top of it. |
| --- | --- |

| Phase 2 | Database Integration |
| --- | --- |

| SUN 07/05 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Learn: What is a database and why do we need one? The problem: right now all data disappears when the app closes. SQLite is a database that stores everything in a single .db file on your computer — no server needed. Read the SQLite JDBC documentation overview. Add the SQLite JDBC Maven dependency to your pom.xml file. |
| --- | --- |

| MON 07/06 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Create DatabaseManager.java in the database package. It has one job: open a connection to the SQLite database file and run the CREATE TABLE IF NOT EXISTS SQL when the app first starts. Test it: run the app, look for the .db file on your computer. Download DB Browser for SQLite (free) and open the file — you should see an empty products table. |
| --- | --- |

| TUE 07/07 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Create ProductDAO.java in the database package. Learn: SQL INSERT with PreparedStatement. Write addProduct(Product p) — it inserts the product's fields into the database using a prepared statement with ? placeholders (never string concatenation — that causes SQL injection). Test: add one product, check DB Browser, confirm the row appears. |
| --- | --- |

| WED 07/08 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: SQL SELECT. Write getAllProducts() in ProductDAO — it runs 'SELECT * FROM products', loops through the ResultSet, and converts each row back into a Product object. Test the most important thing: add 3 products, close the app completely, reopen it, confirm all 3 are loaded. This is data persistence working for the first time. |
| --- | --- |

| THU 07/09 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Learn: SQL UPDATE and DELETE. Write updateProduct(Product p) and deleteProduct(int id) in ProductDAO. Important: deleteProduct now takes an id (from the database), not an ArrayList index. Update InventoryService: instead of storing products in the ArrayList permanently, load them from the database on startup and call the DAO for every add/edit/delete. The ArrayList is now just a temporary in-memory cache. |
| --- | --- |

| FRI 07/10 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Write searchByName(String query) in ProductDAO using SQL LIKE: WHERE name LIKE '%query%'. Write getProductsByCategory(Category cat) using a WHERE clause. Update InventoryService to call these DAO methods instead of filtering the in-memory ArrayList. Test both: search should return the same results as before, just from the database now. |
| --- | --- |

| SAT 07/11 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add error handling to every method in ProductDAO. Every SQL operation is wrapped in a try-catch. If the database cannot be opened (corrupted file, wrong path), show a clear dialog: 'Database error: could not connect. Please check the file exists at [path].' Never let a database error crash the app silently. Test by temporarily renaming the .db file to simulate a missing file. |
| --- | --- |

| SUN 07/12 2 hrs | 10:00 AM – 12:00 PM (2 hrs) PHASE 2 WRAP-UP. Full persistence test: add 5 products of different categories and statuses. Close app. Reopen. Edit one. Delete one. Close again. Reopen. Confirm everything is exactly as expected. Add a comment to every method in DatabaseManager.java and ProductDAO.java. Push with message 'Phase 2 complete: SQLite persistence, full DAO pattern'. |
| --- | --- |

| Phase 3 | GUI Development |
| --- | --- |

| MON 07/13 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: JavaFX basics — Stage, Scene, Node. Create Main.java. It extends Application and overrides start(Stage stage). Set the title to 'Expiration Tracker'. Set a minimum window size (1000x700). Show a single Label that says 'Expiration Tracker - Loading...' in the center. Run it: the goal is just to see a window open and close cleanly. |
| --- | --- |

| TUE 07/14 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: BorderPane, VBox, HBox. Build the main layout: a BorderPane as the root. On the left: a VBox sidebar (width: 180px, dark background color) with navigation labels for Dashboard, Inventory, and Add Product. In the center: an empty VBox placeholder. Style the sidebar with background color using setStyle(). |
| --- | --- |

| WED 07/15 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: TableView and TableColumn. Build the Inventory screen. Create a TableView<Product> with 6 columns: Name, Category, Qty, Expiration Date, Days Left, Status. Populate it with 3 hardcoded Product objects as a test. Set preferred widths for each column. Confirm the table renders with data visible. |
| --- | --- |

| THU 07/16 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Connect the Inventory table to real data. On app startup, call InventoryService.getAllProducts() and load the results into the TableView. Replace the hardcoded test products. Test: data from the database appears in the table. Add color coding to rows: use a TableRow cell factory — red rows for EXPIRED, orange for EXPIRING_SOON, yellow for WARNING, green for SAFE. |
| --- | --- |

| FRI 07/17 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Build the Add Product form. Create a new VBox panel (or Dialog) with labeled input fields: a TextField for Name, a ComboBox for Category (populated from the Category enum), a TextField for Quantity, a DatePicker for Expiration Date, and a TextArea for Notes. Add a 'Save' button and a 'Cancel' button. |
| --- | --- |

| SAT 07/18 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add input validation to the Add Product form. Each field needs an inline error Label (in red, hidden by default) directly below it. When the user clicks Save with an empty Name: show the Name error label. With a non-positive Quantity: show the Quantity error label. With no date selected: show the Date error label. Only save when ALL validations pass. |
| --- | --- |

| SUN 07/19 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Build the Edit Product flow. When the user double-clicks a row in the TableView, the Add/Edit form opens pre-filled with that product's existing data. The Save button now calls InventoryService.editProduct() instead of addProduct(). After saving, the row in the table updates immediately without needing to restart. |
| --- | --- |

| MON 07/20 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Build the Delete flow. Add a 'Delete' button to the toolbar above the TableView (only active when a row is selected). Clicking it opens a JavaFX Alert dialog: 'Delete [product name]? This cannot be undone.' with OK and Cancel buttons. OK calls InventoryService.deleteProduct() and removes the row from the table. Cancel closes the dialog without any changes. |
| --- | --- |

| TUE 07/21 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Build the Dashboard screen. Use a GridPane or FlowPane with 4 stat cards arranged in a row. Each card is a VBox with a large number label and a description label: 'Total Products' (gray), 'Expired' (red background), 'Expiring Soon' (orange background), 'Safe' (green background). Pull real counts from InventoryService. Wire the navigation so clicking 'Dashboard' in the sidebar switches to this screen. |
| --- | --- |

| WED 07/22 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add the 'Expiring This Week' list to the Dashboard. Below the stat cards, add a ListView or a simple VBox showing the top 5 products expiring in the next 7 days, each displaying the product name and days remaining. If there are none, show 'All products are safe this week.' Update the dashboard whenever the inventory changes. |
| --- | --- |

| THU 07/23 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Auto-refresh: whenever a product is added, edited, or deleted, every open screen should update automatically without requiring a restart or manual refresh. Learn about JavaFX ObservableList and how changes propagate to TableView. Use an ObservableList<Product> as the data source — changes to it automatically update the table. Refresh the Dashboard stat cards on every change too. |
| --- | --- |

| FRI 07/24 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Polish the navigation. The currently active screen should be highlighted in the sidebar (different background color). Wire the 'Add Product' sidebar item to open the Add Product form. Make sure navigating between screens does not reset any state — the inventory table should still show the same scroll position when you come back to it. |
| --- | --- |

| SAT 07/25 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) GUI polish session. Review every screen for consistency: are all fonts the same size? Are all buttons the same height and style? Are colors consistent (not 5 different shades of blue)? Are form fields aligned? Fix at least 8 specific visual inconsistencies you find. The goal is a clean, professional look — not fancy, just consistent. |
| --- | --- |

| SUN 07/26 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Full GUI usability test. Use the app as a real user for 30 minutes. Add 12 products across 4 categories, check the dashboard, edit 3 products, delete 2, navigate between all screens. Write down every bug, confusing label, or awkward flow. Prioritize the list: which bugs are blocking (app crashes), which are annoying (wrong behavior), which are minor (cosmetic). |
| --- | --- |

| MON 07/27 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) PHASE 3 WRAP-UP. Fix all remaining 'annoying' bugs from yesterday. Do one final complete test: every button, every screen, every form, every navigation path. Commit with message 'Phase 3 complete: full JavaFX GUI with dashboard, table, add/edit/delete, color coding, auto-refresh'. Tag 'v0.3-gui-complete'. |
| --- | --- |

| Phase 4 | Search, Sort, Filter + Notifications |
| --- | --- |

| TUE 07/28 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add a search bar (TextField) above the inventory table. Add a listener: as the user types each letter, the table immediately filters to show only products whose name contains the typed text. If the search bar is empty, show all products. This must happen on every keystroke with no delay. |
| --- | --- |

| WED 07/29 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: HashMap. Add a Category filter ComboBox next to the search bar. The options are: All Categories + each value from the Category enum. When a category is selected, the table shows only products in that category. The search bar and category filter must work together: if both are active, show products that match BOTH conditions. |
| --- | --- |

| THU 07/30 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Add a Status filter ComboBox: All / Expired / Expiring Soon / Warning / Safe. It must work simultaneously with the search bar and category filter (all 3 active at once). Then add column sorting: clicking a column header sorts that column ascending; clicking again sorts descending. Use a Comparator for each sortable column (Name, Category, Expiration Date, Days Left, Qty). |
| --- | --- |

| FRI 07/31 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: PriorityQueue. Build the startup notification system. When the app opens, scan all products using a PriorityQueue<Product> sorted by daysUntilExpiration. If there are any products with <= 7 days remaining and quantity > 0, show an Alert dialog listing them: 'You have 3 products expiring soon: Milk (2 days), Eggs (5 days), Yogurt (7 days).' |
| --- | --- |

| SAT 08/01 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add a notification badge to the Dashboard. Below the navigation sidebar items, add a red circle badge showing the count of products expiring within 7 days (quantity > 0 only). Update this count in real time: when you add a product expiring in 5 days, the badge increments immediately. When you delete it, the badge decrements. |
| --- | --- |

| SUN 08/02 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Add a 'Clear Filters' button next to the filter bar. Clicking it resets the search text to empty, category to 'All Categories', and status to 'All'. The table immediately shows all products. Also: if no search results match the current filters, show an empty state message inside the table: 'No products match your search.' |
| --- | --- |

| MON 08/03 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Test the entire Phase 4 feature set together. Set all 3 filters, sort by a column, add a new product, edit one, delete one — confirm everything still works correctly when multiple features are active at the same time. Write a list of any bugs or edge cases you find. |
| --- | --- |

| TUE 08/04 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Fix all Phase 4 bugs from yesterday. Then: make the notification system smarter — if a product's quantity is 0, it should NOT appear in the startup alert or the notification badge. It is out of stock and cannot expire on you. Test this rule explicitly. |
| --- | --- |

| WED 08/05 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add keyboard shortcut support. Ctrl+N opens the Add Product form. Ctrl+F focuses the search bar. Pressing Escape while in a form clears the form and closes it. Pressing Delete while a row is selected triggers the delete confirmation. These shortcuts make the app feel professional. |
| --- | --- |

| THU 08/06 4 hrs | 10:00 AM – 2:00 PM (4 hrs) PHASE 4 CHECKPOINT — comprehensive test. Prepare a test scenario: 15 products across all 5 categories and all 4 status levels. Run through every feature: add all 15, test every filter combination, test every sort, test keyboard shortcuts, restart and check notifications, use the Clear Filters button. Document the results. Fix any remaining issues. |
| --- | --- |

| FRI 08/07 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) PHASE 4 WRAP-UP. Clean up all code in InventoryService, ProductDAO, and UI files. Remove any leftover System.out.println debug statements. Ensure all filter, sort, and notification logic has clear comments. Commit with message 'Phase 4 complete: search, sort, filter, notifications, keyboard shortcuts'. Tag 'v0.4-features-complete'. |
| --- | --- |

| Phase 5 | Batch Tracking + Optimization |
| --- | --- |

| SAT 08/08 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn: Code refactoring. Go through InventoryService.java method by method. Find 3 things to improve: (1) any method longer than 30 lines should be split, (2) any duplicated logic should be extracted into a helper, (3) any variable named 'x', 'temp', or 'data' should be renamed to something meaningful. Apply all improvements. |
| --- | --- |

| SUN 08/09 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Create ProductBatch.java in the model package with fields: id, productId, batchLabel (String), quantity, expirationDate (LocalDate), receivedDate (LocalDate), supplier (String), notes (String). Add getDaysUntilExpiration() and isExpired() methods — same logic as in Product but operating on the batch's own expirationDate. |
| --- | --- |

| MON 08/10 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Write addBatch(ProductBatch b) and getBatchesForProduct(int productId) in ProductDAO. addBatch() inserts a new row into product_batches. getBatchesForProduct() retrieves all rows where product_id matches, ordered by expiration_date ASC (oldest batch first — FIFO order). Test with one product and 2 batches. |
| --- | --- |

| TUE 08/11 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add batch support to the Add Product form. After filling in the main product fields and clicking Save, a second step appears: 'Add Batch Details'. Fields: Batch Label (optional, e.g. 'June 8 Delivery'), Quantity for this batch, Expiration Date for this batch, Supplier (optional). Save both the product and the batch in one operation. |
| --- | --- |

| WED 08/12 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add a 'View Batches' button to the Inventory table toolbar (active only when a product with batches is selected). Clicking it opens a small popup window listing all batches for that product as a table: Batch Label ¦ Quantity ¦ Received ¦ Expires ¦ Days Left ¦ Status. Batches are sorted oldest first. |
| --- | --- |

| THU 08/13 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Update the notification system to check batch-level expiration instead of product-level. A product should trigger an alert if ANY of its active batches expire within 7 days AND that batch has quantity > 0. A product with zero-quantity batches: no alert. Test with a product that has 2 batches: one expiring in 3 days (qty=2) and one in 20 days (qty=5). Only the first should alert. |
| --- | --- |

| FRI 08/14 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add the inventory_movements table to the database. Create InventoryMovement.java with fields: id, productId, batchId, movementType (enum: RECEIVE, USE, DISCARD, ADJUST), quantityChange (positive or negative), movementDate, staffNote. Write addMovement() in ProductDAO. |
| --- | --- |

| SAT 08/15 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Dedicated bug-hunting session. Open the app and systematically try to break every feature. Focus on batch features: what happens if you add a product with no batches? What if you delete a product that has batches? What if a batch has 0 quantity and expires today? Write down every crash or wrong behavior. Fix each one. |
| --- | --- |

| SUN 08/16 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Performance test. Write a quick script (in a test main method) that adds 200 products to the database with 2 batches each. Then time how long the app takes to start, load the table, run a search, and apply a filter. If anything takes more than 2 seconds, investigate whether it is a slow SQL query or a UI rendering issue. |
| --- | --- |

| MON 08/17 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) UI improvements for batch-aware features. Update the Inventory table to show the soonest-expiring batch date (not the product creation date) in the Expiration Date column. Update the Status column to reflect the most urgent batch's status. The table should always show worst-case status for each product. |
| --- | --- |

| TUE 08/18 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add a 'SOLD OUT' visual indicator in the inventory table for products where all batches have quantity = 0. They should appear faded gray, not colored by status, and should not appear in the notification badge count. This is a UX improvement: sold-out items are visually distinct from active inventory. |
| --- | --- |

| WED 08/19 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) PHASE 5 WRAP-UP / CORE DEADLINE. Full end-to-end test: launch app, add 5 products with batches, check notifications, use search + filters + sort, view batches popup, check performance. Every feature from Phase 0 through 5 must work. Fix any final bugs. Commit 'Phase 5 complete: batch tracking, movement log, optimization'. Tag 'v0.5-core-complete'. |
| --- | --- |

| Phase 6 | OCR + Receipt Scanning |
| --- | --- |

| THU 08/20 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Install Python 3, Tesseract OCR engine, and the Python libraries pytesseract and Pillow. Verify the installation: run 'python3 -c "import pytesseract; print(pytesseract.get_tesseract_version())"' in terminal. Then write a standalone Python script (ocr_test.py) that opens a receipt image and prints all extracted text to the console. Do not integrate with Java yet — just get the OCR working in Python first. |
| --- | --- |

| FRI 08/21 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Write the Java-to-Python bridge. Create OcrService.java in the service package. It uses ProcessBuilder to run the Python OCR script as a subprocess, passing the image file path as a command-line argument. Read the standard output from Python line by line and return it as a List<String>. Test: call it from a Java main method and print the extracted lines. |
| --- | --- |

| SAT 08/22 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Write the text parser. The raw OCR output contains everything on the receipt: store name, prices, totals, dates, addresses. Write cleanOcrOutput(List<String> lines) in OcrService that filters out obvious non-product lines (lines that are all numbers, lines shorter than 3 characters, lines that are prices like '$4.99', lines that are common receipt headers like 'TOTAL' or 'SUBTOTAL'). Return only likely product names. |
| --- | --- |

| SUN 08/23 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Learn: HashSet for deduplication. If the same product name appears twice in the OCR output, a HashSet automatically ignores the duplicate. Wrap the cleaned OCR results in a LinkedHashSet<String> (preserves insertion order while preventing duplicates). Test with a receipt that has the same item twice. |
| --- | --- |

| MON 08/24 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add a 'Scan Receipt' button to the toolbar in the Inventory screen. Clicking it opens a FileChooser dialog filtered to image files (.jpg, .png, .jpeg). When a file is selected, call OcrService to process it. Show a loading indicator (a ProgressIndicator or a status label 'Scanning...') while OCR runs so the user knows the app is working. |
| --- | --- |

| TUE 08/25 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Build the OCR Review screen. After scanning, show a new panel listing all extracted product names. Each entry has: a Checkbox (checked by default), the product name in a TextField (editable), and a Remove button. The user reviews the list, unchecks anything they do not want to add, edits any misread names, then clicks 'Add Selected to Inventory'. |
| --- | --- |

| WED 08/26 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Handle OCR failures. Test these failure cases and add appropriate error handling for each: (1) image file cannot be read — show 'Could not open file. Is it a valid image?', (2) Python is not installed or not found — show 'OCR requires Python 3. Please install it and try again.', (3) OCR extracts nothing useful — show 'No readable text found. Try a clearer photo with better lighting.' |
| --- | --- |

| THU 08/27 4 hrs | 10:00 AM – 2:00 PM (4 hrs) OCR accuracy testing session. Collect 5 receipts (photograph them with your phone — store receipt, pharmacy receipt, convenience store receipt if possible). Run each through the app. Record results: how many lines total, how many were products, how many were correctly extracted, how many were missed. Improve the Python text parser based on what you learn. |
| --- | --- |

| FRI 08/28 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Improve the Python OCR parser with name cleaning: convert all extracted names to Title Case (e.g. 'WHOLE MILK 1GAL' becomes 'Whole Milk'), remove common trailing patterns like weights (1GAL, 12OZ, 2LB), remove SKU codes (all-caps 6+ character strings with numbers). The goal: names that look like what you would type into the app manually. |
| --- | --- |

| SAT 08/29 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) FEATURE COMPLETE DEADLINE. Full end-to-end test of every feature: start app, check dashboard, add product, view inventory, search, filter, sort, keyboard shortcuts, batch tracking, scan receipt. Every single feature must work. Fix any blocking issues. Commit 'Phase 6 complete: OCR receipt scanning, review screen, error handling'. Tag 'v0.6-feature-complete'. |
| --- | --- |

| SUN 08/30 2 hrs | 10:00 AM – 12:00 PM (2 hrs) Buffer day. If everything passed yesterday: review your README and start planning the Phase 7 test cases. If anything still needs fixing from Phase 6: use this entire session to fix it. Nothing from Phase 7 starts until Phase 6 is truly complete. |
| --- | --- |

| MON 08/31 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Extra buffer and prep day. Review all code you wrote in Phases 5 and 6. Write the full Phase 7 test plan: 20 specific test cases, each written as 'Given [setup], When [action], Then [expected result]'. This structured format makes testing faster and more reliable. |
| --- | --- |

| Phase 7 | Finalization + Documentation |
| --- | --- |

| TUE 09/01 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Execute test cases 1–7 from your test plan. For each test: set up the scenario, perform the action, record Pass or Fail, and write the exact failure description if it failed. Do not fix anything yet — run all tests first, then fix. The goal is a complete picture of the app's state before you start changing things. |
| --- | --- |

| WED 09/02 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Fix all Critical and Major test failures from yesterday. A Critical failure (crash, data loss) must be fixed before any other work. A Major failure (wrong behavior) gets fixed today. If fixing a bug takes more than 30 minutes, write down what you tried and move to the next bug — come back after fixing the others. |
| --- | --- |

| THU 09/03 4 hrs | 10:00 AM – 2:00 PM (4 hrs) Write README.md. It must include: (1) Project title and one-paragraph description, (2) Screenshot of the dashboard, (3) Screenshot of the inventory table, (4) Installation instructions — exactly what to install and in what order, (5) How to use the app — a short walkthrough, (6) Tech stack table (Java, JavaFX, SQLite, Python, Tesseract), (7) What you learned building this. Aim for a README someone else could follow without asking you any questions. |
| --- | --- |

| FRI 09/04 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Add comments to every class and every method. The comment format: what does this method do (one sentence), what does each parameter mean, what does it return. Focus on the methods that are not obvious — addProduct() is clear, but the OCR text parser and the PriorityQueue scanner benefit from explanation. Aim for 100% of public methods commented. |
| --- | --- |

| SAT 09/05 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Learn about jpackage (included with JDK 14+). Create a packaged installable for your operating system: Windows (.exe installer), macOS (.dmg), or Linux (.deb). The packaged app must open without IntelliJ and must find its database file in the user's home directory. Test the installer on your machine — install it, open it, confirm it works exactly like running from IntelliJ. |
| --- | --- |

| SUN 09/06 2 hrs | 10:00 AM – 12:00 PM (2 hrs) GitHub cleanup. Delete all feature branches that have been merged. Add a .gitignore file covering Java, IntelliJ, macOS, and Windows artifacts. Remove any accidental committed files: .idea folders, .db files (database should not be in version control), target/ or out/ build folders. Preview your README on GitHub — does it look professional? |
| --- | --- |

| MON 09/07 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Prepare your demo. Write a 5-minute script that tells a story: 'Imagine you just went grocery shopping. You have 10 items, some of which expire soon...' Walk through adding products, checking the dashboard, filtering expiring items, scanning a receipt, and receiving a notification. Practice speaking the script out loud while using the app. Time yourself. |
| --- | --- |

| TUE 09/08 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Final bug sweep. Open the app and use every single feature one last time. Focus on transitions: what happens right after you delete a product? Right after you scan a receipt? Right after the app opens? Edge cases in transitions are where bugs hide. Fix any issue you find. After this session, the feature set is FROZEN — no new changes, only crash fixes. |
| --- | --- |

| WED 09/09 2.5 hrs | 10:00 AM – 12:30 PM (2.5 hrs) Fix any remaining Minor test failures (cosmetic bugs) if time allows. Write a brief Architecture Notes document explaining: the three-layer design, the class relationships, the database schema, why you made the key technical decisions. This is for your own future reference and for portfolios. |
| --- | --- |

| THU 09/10 4 hrs | 10:00 AM – 2:00 PM (4 hrs) FINAL DEADLINE. Tag 'v1.0-final'. Run the app one last time from the installer — not IntelliJ, the actual packaged installer. Confirm it works perfectly. Open your GitHub repository and read it as if you are seeing it for the first time — is it clear what this project is? Are the screenshots up to date? Is the README accurate? Make any last corrections. You are done. Reflect: what did you build? What did you learn? What would you do differently? |
| --- | --- |